## Gantt Chart Template
Gantt Chart Template
| COMPANY NAME | [7 empty] | PROJECT MANAGER
| PROJECT TITLE | [7 empty] | DATE
START DATE
END DATE
[9 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | STATUS | PREDECESSOR (WBS NUMBER) | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[9 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation | [5 empty] | Green
1.1 | Project Charter | Amber | 2023-03-12 | 2023-03-15 | 3 | 100% | Completed | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | Amber | 2023-03-15 | 2023-03-16 | 1 | 100% | Completed | 1.1 | bar: WEEK 2 W
1.2 | Research | Martin | 2023-03-15 | 2023-03-21 | 6 | 90% | Green | 1.1 | bar: WEEK 2 W to WEEK 3 W
1.3 | Projections | Martin | 2023-03-16 | 2023-03-22 | 6 | 40% | Yellow | bar: WEEK 2 R to WEEK 3 R
1.4 | Steering Committee Meetings | Amber | 2023-03-18 | 2023-03-22 | 4 | 70% | Green | bar: WEEK 3 M to WEEK 3 R
1.5 | Guidelines | Martin | 2023-03-19 | 2023-03-22 | 3 | 60% | Green | 1.4 | bar: WEEK 3 T to WEEK 3 R
1.6 | Project Initiation Completed | Amber | 2023-03-23 | 2023-03-23 | 0 | 50% | Green | bar: WEEK 3 F
2 | Project Definition and Planning | [5 empty] | Green
2.1 | Scope & Goal Setting | Martin | 2023-03-24 | 2023-03-28 | 4 | 22% | Green | 1.6 | bar: WEEK 4 M to WEEK 4 R
2.2 | Budget Approved | Amber | 2023-03-29 | 2023-04-02 | 3 | 16% | Red | bar: WEEK 4 F to WEEK 5 F
2.3 | Communication Plan Approved | Amber |  |  | 0 | 0% | Not started
2.4 | Risk Management | Amber |  |  | 0 | 0% | Not started
2.5 | Project Definition and Planning Completed | Amber |  |  | 0 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Martin |  |  | 0 | 0%
3.2 | KPIs | Amber |  |  | 0 | 0%
3.2.1 | Monitoring | Amber |  |  | 0 | 0%
3.2.2 | Forecasts Completed | Amber |  |  | 0 | 0%
3.3 | Project Updates | Martin |  |  | 0 | 0%
3.3.1 | Chart Updates | Amber |  |  | 0 | 0%
3.4 | Project Launch & Execution Completed | Amber |  |  | 0 | 0%
4 | Project Performance/Monitoring
4.1 | Review Project Objectives | Martin |  |  | 0 | 0%
4.2 | Quality Deliverables | Martin |  |  | 0 | 0%
4.3 | Effort & Cost Tracking | Amber |  |  | 0 | 0%
4.4 | Project Performance | Amber |  |  | 0 | 0%
5 | Project Closure
5.1 | Coordinate Wrap Up Meeting | Amber |  |  | 0 | 0%
5.2 | Document Learnings | Amber |  |  | 0 | 0%
5.3 | Release Resources | Amber |  |  | 0 | 0%
5.4 | Formal Project in Tools/Notify Finance | Amber |  |  | 0 | 0%
5.5 | Project Closure Completed | Amber |  |  | 0 | 0%
Legend:
Not started | Task hasn't been started yet
Green | On track, no current issues
Yellow | There is a risk or problem impacting the project, correction needed
Red | Project is blocked. One of the project dimensions (scope/time/budget) will not be met. Potential need for management intervention.
Completed | Task completed
Ongoing | Ongoing tasks throughout the project